## Detailed Workplan
Attachment 2: SAFE PROGRAM CONTRACT FARMING AND PRODUCE BUYING NETWORK PARTNERSHIP
Sheet 2 of 3
Name of Contract farming and Produce buying Company:
Period of Performance:
Note: If the activities listed in the SOW is revised, the activities in this budget has to be revised as well so that the activities in both documents are matching.
EXPANSION OF CONTRACT FARMING AND AGRICULTURE PRODUCE MARKET NETWORKS AND IN SOUTH KORDOFAN, SUDAN
| Activity Description | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14
1 | Main Activity 1: mobilization and sensitization of community leaders, government officials and select community 20 contract farming agents
1.1 | Meet leaders of communities and farmer groups and government officials
1.2 | Sensitise communities and farmer groups
1.3 | Identify contract farming company agents:
1.4 | Train contract farming community farming agents
1.5 | 1.5 Equip contract farming agents to promote contract farming among smallholder farmers
1.6
1.7
2 | Main Activity 2: Register and Contract of 3,000 farmers
2.1 | Register and contract 2,000 farmers through agreements
2.2
2.3
3 | Main Activity 3: Provide pre-season agriculture extension training to 80 groups containing 2,000 farmers and establish 80 demonstration plots
3.1 | Conduct agriculture extension training to 2,000 farmers
3.2 | Set up 80 demonstration training plots and use them to train farmers
3.3 | 3.3 Provide 2,000 A-4 sized agronomic and crop management guide poster
3.4
4 | Main Activity 4: Provide subsidised seeds to 2,000 farmers and support them to plant at least one feddan each.
4.1 | 4.1 Provide certified seeds at a subsdised price to 2,000 farmers on credit
4.2
4.3
4.4
5 | Main Activity 5; Provide crop management training to 80 groups containing 2,000 farmers to manage at least 2,000 feddans.
5.1 | Contract farming agents conduct second technical training to 80 groups containing farmers
5.2
5.3
5.4
6 | Main Activity 6: Develop a network of 20 entrepreneurial males and females produce buying agents.
6.1 | Select and train male and female community level produce buying agents
6.2 | Develop and equip produce buying agents with produce quality guidance manuals
6.3 | Train produce buying agents on business skills and produce sourcing
6.4
7 | Main Activity 7: Buy agriculture produce from the small-scale farmers
7.1 | Equip buying agents to check the quality of produce and buy produce from farmers
7.2 | Support agents to mobilize produce from farmers and aggregate it for sale
7.3
7.4
7.4
PARTNERSHIP TOTAL